## Summary
Overall Status
Date | 2020-06-24
Team Member | Done | WIP | YTS
iAssureIT | 92.86% | 0% | 7.143%
Ashish Chavan | 0% | 66.67% | 33.33%
Ranjan Zha | 8.824% | 13.24% | 77.94%
Manish Kulkarni | 0% | 33.33% | 66.67%
Avinash Gaikwad | 0% | 50% | 50%
Total | 28.71% | 23.27% | 48.02%
Team Member | %age alloation
iAssureIT | 27.72%
Ashish Chavan | 14.85%
Ranjan Zha | 33.66%
Manish Kulkarni | 17.82%
Avinash Gaikwad | 5.941%

## DSR
Daily Status Report
Status as of date: | 2020-06-24
Overall Project
| Planned Start Date | 2020-06-01 | Planned End date | 2020-07-16
| Actual Start Date | 2020-06-01 | Actual End date
| Days Planned | 34 | Days Elapsed | 18
| Planned completion (Size) | 205 | Completion till date (Size) | 116
| Planned %age completion | 50.74% | %age Completion | 28.71%
TruU Website & Post login Features
| Planned Start Date | 2020-06-01 | Planned End date | 2020-06-30
| Actual Start Date | 2020-06-01 | Actual End date
| Days Planned | 22 | Days Elapsed | 18
| Planned completion (Size) | 83 | Completion till date (Size) | 11
| Planned %age completion | 53.55% | %age Completion | 7.097%
Admin Web App
| Planned Start Date | 2020-06-01 | Planned End date | 2020-07-16
| Actual Start Date | 2020-06-01 | Actual End date
| Days Planned | 34 | Days Elapsed | 18
| Planned completion (Size) | 122 | Completion till date (Size) | 105
| Planned %age completion | 49% | %age Completion | 42.17%
Summary |  | %age Distribtion
TruU Website & Post login Features
Done | 11 | 7.097%
WIP | 48 | 30.97%
YTS | 96 | 61.94%
Total | 155
Summary |  | %age Distribtion
Admin Web App
Done | 105 | 42.17%
WIP | 46 | 18.47%
YTS | 98 | 39.36%
Total | 249

## Team Member
Summary for Team Members
Status as of date: | 2020-06-24
Team Member | iAssureIT
| Allocated | Done | WIP | YTS
TruU Website & Post login Features | 11 | 11 | 0 | 0
Admin Web App | 101 | 93 | 0 | 8
Total | 112 | 104 | 0 | 8
Team Member | Ashish Chavan
| Allocated | Done | WIP | YTS
TruU Website & Post login Features | 60 | 0 | 40 | 20
Admin Web App | 0 | 0 | 0 | 0
Total | 60 | 0 | 40 | 20
Team Member | Ranjan Zha
| Allocated | Done | WIP | YTS
TruU Website & Post login Features | 48 | 0 | 8 | 40
Admin Web App | 88 | 12 | 10 | 66
Total | 136 | 12 | 18 | 106
Team Member | Manish Kulkarni
| Allocated | Done | WIP | YTS
TruU Website & Post login Features | 24 | 0 | 0 | 24
Admin Web App | 48 | 0 | 24 | 24
Total | 72 | 0 | 24 | 48
Team Member | Avinash Gaikwad
| Allocated | Done | WIP | YTS
TruU Website & Post login Features | 12 | 0 | 0 | 12
iAssure International Technologies Pvt Ltd www.iassureit.com ¦ ashish.naik@iassureit.com ¦ +91-99233 93733 | 12 | 0 | 12 | 0
Total | 24 | 0 | 12 | 12

## Website
iAssure International Technologies Pvt Ltd www.iassureit.com ¦ ashish.naik@iassureit.com ¦ +91-99233 93733
TruU Website & Post login Features
Feature Item | Total Efforts (In days) | Size (Points) | Status | Developer | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Schedule Adherence
System Security
SignUp / Register User Mobile Number Verification: Send OTP thru SMS. (Mandatory) Email Verification: Send OTP thru Email. (Mandatory) | 1 | 4 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
OTP Validation Screen | 0.5 | 2 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
Login Screen | 12 | 3 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
Forgot Password | 0.5 | 2 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
Web Pages
Home Page | 2 | 8 | WIP | Ashish Chavan | 2020-06-03 | 2020-06-04 | 2020-06-03 | 2020-06-04 | Met
SEO Friendly Work on Each Page | 2 | 8 | YTS | Ashish Chavan | 2020-06-15 | 2020-06-16
How It Works | 1 | 4 | YTS | Ashish Chavan | 2020-06-22 | 2020-06-22
About | 1 | 4 | YTS | Ashish Chavan | 2020-06-23 | 2020-06-23
Contact | 1 | 4 | YTS | Ashish Chavan | 2020-06-24 | 2020-06-24
Patient Dashboard
My Accountc - UI Development | 0.5 | 2 | WIP | Ranjan Zha | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04
My Appointments - UI Development | 0.5 | 2 | WIP | Ranjan Zha | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04
Financial Documents - UI Development | 0.5 | 2 | WIP | Ranjan Zha | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-06-05
Messages - UI Development | 0.5 | 2 | WIP | Ranjan Zha | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-06-05
My Account - API Development & Integration with UI | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-12 | 2020-06-12
My Appointments - API Development & Integration with UI | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-12 | 2020-06-12
Financial Documents - API Development & Integration with UI | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-15 | 2020-06-15
Messages - API Development & Integration with UI | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-15 | 2020-06-15
Make an appointment
Get Started Block on Website | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-16 | 2020-06-16
Sign Up Form | 0.25 | 1 | YTS | Ranjan Zha | 2020-06-16 | 2020-06-16
OTP Validation Form | 0.25 | 1 | YTS | Ranjan Zha | 2020-06-16 | 2020-06-16
Map Page to display Van locations on various days | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-17 | 2020-06-17
Display Appointment Schedule for any selected date | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-17 | 2020-06-17
Select Appointment | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-18 | 2020-06-18
Add to Wishlist Page | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-18 | 2020-06-18
Add to Wishlist Form | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-19 | 2020-06-19
Insurance Details Form | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-19 | 2020-06-19
Confirmation Message after appointment is scheduled | 0.25 | 1 | YTS | Ranjan Zha | 2020-06-22 | 2020-06-22
Thank You Message | 0.25 | 1 | YTS | Ranjan Zha | 2020-06-22 | 2020-06-22
Waiting number is converted into appointment. Display this new appointment in the list of appointments from admin side and patient side. Discuss this with Client | 1 | 4 | YTS | Ranjan Zha | 2020-06-26 | 2020-06-26
Virtual Waiting Room For appointments, check in patients into virtual waiting room a half hour before the truck gets there, may be the patients can communication over text with truU, then send another message once truck is ready to see them. Goal is to ensure the patients arent standing somewhere waiting for truck and vice versa. The desire is to somehow either tie it to the truck's GPS location (and estimate that it is a half hour away) or manually triggered by truck staff that they're a half hour away Discuss this with Client | 2 | 8 | YTS | Ranjan Zha | 2020-06-29 | 2020-06-30
Virtual Consult
Form to Contact Doctor Select service, write message, attach Video, Audio, Image, PDF, etc | 1 | 4 | WIP | Ashish Chavan | 2020-06-02 | 2020-06-22
List of all Consultations | 1 | 4 | WIP | Ashish Chavan | 2020-06-23 | 2020-06-23
Events
Display Events Locations with dates on Map | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-22 | 2020-06-22
Responsive & Cross Browser Compatibility
Responsive Pages | 1 | 12 | WIP | Ashish Chavan | 2020-06-25 | 2020-06-25
Cross Browser Compatibility | 1 | 12 | WIP | Ashish Chavan | 2020-06-26 | 2020-06-26
Graphic Design | 3 | 12 | YTS | Avinash Gaikwad
Requirement Analysis, Database Design & System Architecture | 3 | 12 | YTS | Manish Kulkarni
BRD, FSD Documentation | 3 | 12 | YTS | Manish Kulkarni
Total Development Efforts (In Person Days) | 32

## Admin Web App Features
iAssure International Technologies Pvt Ltd www.iassureit.com ¦ ashish.naik@iassureit.com ¦ +91-99233 93733
Admin Web App
Feature Item | Total Efforts | Size - Points | Status | Developer | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Schedule Adherence
System Security
SignUp / Register User Mobile Number Verification: Send OTP thru SMS. (Mandatory) Email Verification: Send OTP thru Email. (Mandatory) | 0.5 | 2 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
OTP Validation Screen | 0.5 | 2 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
Login Screen | 0.5 | 2 | Done | iAssureIT | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 | Met
Forgot Password | 0.5 | 2 | Done | iAssureIT | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 | Met
Project Preparation
Setup Domain & SubDomains | 1 | 4 | YTS | Manish Kulkarni
SetUp Email ID (If domain is not available, use gmail id) | 1 | 4 | YTS | Manish Kulkarni
Setup Plivo.com SMS Gateway and obtain SMS gateway Credentials | 1 | 4 | YTS | Manish Kulkarni
Setup Amazon S3 Account and obtain S3 Bucket Details | 1 | 4 | YTS | Manish Kulkarni
Setup Google API Account and obtain Google API KeY Details | 1 | 4 | YTS | Manish Kulkarni
Setup GitHub Account and create new repository. Assign access to team members. | 1 | 4 | YTS | Manish Kulkarni
Organization Setting
Organization Basic info & Logo | 1 | 4 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
Organization Locations | 1 | 4 | Done | iAssureIT | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 | Met
Organization Contact Details | 1 | 4 | Done | iAssureIT | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Met
Organization Profile | 1 | 4 | Done | iAssureIT | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04 | Met
Master Data
SMS Gateway Configuration Keys | 1 | 4 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
Amazon S3 Configuration Keys | 1 | 4 | Done | iAssureIT | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 | Met
Location Types | 1 | 4 | Done | iAssureIT | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Met
Department | 1 | 4 | Done | iAssureIT | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04 | Met
Designation | 1 | 4 | Done | iAssureIT | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-06-05 | Met
User Management
Add User from Admin side Admin will add multiple user like Faculty/Team member and executive management from variuos department according to their acess criteria . | 1 | 4 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
List of users Admin can view all the user with their department. This list will have all required filters such as Show Role wise users, status wise users, department wise, etc List will have bulk user update facility. | 1 | 4 | Done | iAssureIT | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 | Met
Edit user | 0.5 | 2 | Done | iAssureIT | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Met
Delete user If user has some transactions in the system, that user can't be deleted. | 0.1 | 1 | Done | iAssureIT | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Met
Block user Admin can block a single user or multiple users at a time. Blocked users can not login to system. | 0.1 | 1 | Done | iAssureIT | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Met
Activate user Admin can activate the blocked user | 0.1 | 1 | Done | iAssureIT | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Met
Search User | 0.4 | 2 | Done | iAssureIT | 2020-06-03 | 2020-06-04 | 2020-06-03 | 2020-06-04 | Met
List of Deleted Users | 1 | 4 | Done | iAssureIT | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04 | Met
Ability to recover the deleted user | 1 | 4 | Done | iAssureIT | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-06-05 | Met
Ability to permanently delete the user | 0.5 | 2 | Done | iAssureIT | 2020-06-08 | 2020-06-08 | 2020-06-08 | 2020-06-08 | Met
Notification Module
Create Templates for Mail, SMS & InAPP Notifications | 1 | 4 | Done | iAssureIT | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
List of all Notification Templates for Mail, SMS & InAPP | 1 | 4 | Done | iAssureIT | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 | Met
Edit & Delete Facility of all Notification Templates | 1 | 4 | Done | iAssureIT | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Met
Ability to map the Event with Roles and Templates | 1 | 4 | Done | iAssureIT | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04 | Met
Ability to switch on or off any kind of Notification | 1 | 4 | Done | iAssureIT | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-06-05 | Met
In-App Notification Display after User Login | 1 | 4 | Done | iAssureIT | 2020-06-08 | 2020-06-08 | 2020-06-08 | 2020-06-08 | Met
Eventwise Notifications to be sent to user using templates | 2 | 8 | YTS | iAssureIT | 2020-07-09 | 2020-07-12
Patient Master
Add New Patient | 1 | 4 | Done | Ranjan Zha | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | Met
List of Patients | 1 | 4 | Done | Ranjan Zha | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 | Met
Edit / Delete of Patients | 1 | 4 | Done | Ranjan Zha | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-03 | Met
Create Login functionality for Patients | 1 | 4 | WIP | Ranjan Zha
Display Patients on Map using their Home Locations | 1 | 4 | WIP | Ranjan Zha
Appointment Management
Create Appointment Slots Using Day, Duration, Start & End Time of the working hours, you generate Appointment slots. User can delete some appointments. Later User can submit these slots to database. Add Area Field. Integrate that fireld with Google Location API and select only Area names. You will get Lat/Long of the Area in background. | 0.5 | 2 | WIP | Ranjan Zha | 2020-06-09 | 2020-06-09 | 2020-06-09 |  | Met
List of all available appointment slots | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-09 | 2020-06-09
Edit or Delete any appointment | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-10 | 2020-06-10
Disable certain Appointment slots in any day or for whole day. Change status of Appointment to "Inactive" | 0.25 | 1 | YTS | Ranjan Zha | 2020-06-10 | 2020-06-10
Clone Appointment Schedule for whole day Use can clone the whole day Appointment Schedule as it is. | 0.5 | 2 | YTS | Ranjan Zha | 2020-06-11 | 2020-06-11
Below features will happen after Patient will select the required Appointment from Frontend.
List of only Patient appointments | 1 | 4 | YTS | Ranjan Zha | 2020-06-23 | 2020-06-23
Ability to put appointment for any patient | 1 | 4 | YTS | Ranjan Zha | 2020-06-24 | 2020-06-24
Search Any appointment for any patient | 1 | 4 | YTS | Ranjan Zha | 2020-06-25 | 2020-06-25
Event Management Let's add one more here: selectively display events in a public setting
Create New Event Some events are going to for some employers only - and not shown publicly if they want that way | 1 | 4 | YTS | Ranjan Zha | 2020-07-01 | 2020-07-01
List of all Events | 1 | 4 | YTS | Ranjan Zha | 2020-07-02 | 2020-07-02
Edit & Delete of the Events | 0.75 | 3 | YTS | Ranjan Zha | 2020-07-03 | 2020-07-03
Classify Events as per Date, Places, Occurance | 0.5 | 2 | YTS | Ranjan Zha | 2020-07-03 | 2020-07-06
Show Number of Patients for the completed Events | 0.5 | 2 | YTS | Ranjan Zha | 2020-07-06 | 2020-07-06
When clicked on number of patients, show the list of all patients | 1 | 4 | YTS | Ranjan Zha | 2020-07-07 | 2020-07-07
Display Events on Map | 2 | 8 | YTS | Ranjan Zha | 2020-07-08 | 2020-07-09
Reporting System
All Appointments Report Daily, Weekly, Monthly, Yearly & Custom Date Range Report Filters with Places, Events, Dental Services, etc | 2 | 8 | YTS | Ranjan Zha | 2020-07-10 | 2020-07-13
Dashboards for Admin
Admin Dashboard with Various blocks and Statistics as required | 3 | 12 | YTS | Ranjan Zha | 2020-07-14 | 2020-07-16
Graphic Design | 3 | 12 | WIP | Avinash Gaikwad
Requirement Analysis, Database Design & System Architecture | 3 | 12 | WIP | Manish Kulkarni
BRD, FSD Documentation | 3 | 12 | WIP | Manish Kulkarni
Total Development Efforts (In Person Days) | 61.7

## Pending Tasks
Sr. No. | Module Name | Task | Task Owner | Status | Effort | Planed Start Date | Planed End Date | Actual Start Date | Actual End Date
1 | eCommerce Website | On "Home Page" How application will behave if application will have more than 4 sections. | Ashish Sir | YTS
2 | eCommerce Website | Check whether valid sub sections displays in the list when user hover mouse on section menu. | Oshin | YTS
3 | eCommerce Website | When click on sub section menu, Check product displays on the page are related to the clicked section. | Oshin | YTS
4 | eCommerce Website | Redesign "Search Page" design. | Omkar | YTS
5 | eCommerce Website | Search functionality on "Search Page" is not working. | Omkar | YTS
6 | eCommerce Website | All pages should have "Home" page icon when user navigate to other pages. Refer https://www.mi.com/in | Ashish Sir | YTS
7 | eCommerce Website | Check auto slide functionaliy of banner. It slides only ones. |  | Done
8 | eCommerce Website | On "Home Page " Add "<" & ">" buttons in to the banner for banner navigation. | Priya | YTS
9 | eCommerce Website | On "Home Page Require contain & images for banner from client. | Manish | YTS
10 | eCommerce Website | On "Home Page "View Details" button on banner is not working. | Ashish Sir | YTS
11 | eCommerce Website | On "Home Page On banner, when clicks on cards, click functionality is not working. | Ashish Sir | YTS
12 | eCommerce Website | On "Home Page" "Offers" functionality is not available. (Refer Bhajiwala.com) | Ashish Sir | YTS
13 | eCommerce Website | On "Home Page" "Best Deals" functionality is not available. (Refer Bhajiwala.com) | Ashish Sir | YTS
14 | eCommerce Website | On "Home Page" "New Arrival" functionality is not available. (Refer Bhajiwala.com) | Ashish Sir | YTS
15 | eCommerce Website | On "Home Page Require contain from client for "We are fresh food" . | Manish | YTS
16 | eCommerce Website | On "Home Page "Shop By Category" section Image size for all images is not equal. | Priya | Done
17 | eCommerce Website | On "Home Page "Shop By Category" section How application will behave if application will have more than 8 categories. | Ashish Sir | YTS
18 | eCommerce Website | On "Home Page "Shop By Category" section When click on product category, page should display products related to clicked category. | Oshin | YTS
19 | eCommerce Website | on "Home Page" at "Big Sale" section Is contain of this section static or dynamic? If dynamic we need contain management system. | Ashish Sir | YTS
20 | eCommerce Website | on "Home Page" at "Big Sale" section Click on "Shop Now" button you are redirected to the same page. What is required functionality? | Ashish Sir | YTS
21 | eCommerce Website | Require contain for "WHY CHOOSE US" from client. | Manish | YTS
22 | eCommerce Website | On "Home Page" at "Latest From Blog" section "See All" is not a text, it's link. When user clicks on this link, page will display with all blogs. | Ashish Sir | YTS
23 | eCommerce Website | On "Home Page" at "Latest From Blog" section Auto slid functionality should be there when application have more than 3 blogs. | Ashish Sir | YTS
24 | eCommerce Website | On "Home Page" at "Latest From Blog" section Add "<" and ">" buttons when application have more than 3 blogs. | Ashish Sir | YTS
25 | eCommerce Website | On "Home Page" at "Latest From Blog" section When mouse hovers on blog image it should change to hand. Refer Product image. | Ashish Sir | YTS
26 | eCommerce Website | On "Home Page" at "Latest From Blog" section When click on blog image or blog name clicked blog should display. | Ashish Sir | YTS
27 | eCommerce Website | On "Home Page" at "Footer" How to read complete contain of "About Us" section? | Mandar Sir | YTS
28 | eCommerce Website | On "Home Page" at "Footer" Require contain for "About Us" section from client. | Manish | YTS
29 | eCommerce Website | On "Home Page" at "Footer" "Delivery" link is not working. | Mandar Sir | YTS
30 | eCommerce Website | On "Home Page" at "Footer" "Legal Notice" link is not working. | Mandar Sir | YTS
31 | eCommerce Website | On "Home Page" at "Footer" "About US" link is not working. | Mandar Sir | YTS
32 | eCommerce Website | On "Home Page" at "Footer" "Secure Payment" link is not working. | Ashish Sir | YTS
33 | eCommerce Website | On "Home Page" at "Footer" "Our Stores" link is not working. | Ashish Sir | YTS
34 | eCommerce Website | On "Home Page" at "Footer" "Contact Us" link is not working. | Mandar Sir | YTS
35 | eCommerce Website | On "Home Page" at "Footer" "Terms of Use" link is not working. | Mandar Sir | YTS
36 | eCommerce Website | On "Home Page" at "Footer" "Privacy Policy" link is not working. | Mandar Sir | YTS
37 | eCommerce Website | On "Home Page" at "Footer" "Site Map" link is not working. | Ashish Sir | YTS
38 | eCommerce Website | On "Home Page" at "Footer" What is the functionality of "Language" link. | Ashish Sir | YTS
39 | eCommerce Website | On "Home Page" at "Footer" What is the functionality of "Price" link. | Ashish Sir | YTS
40 | eCommerce Website | On "Home Page" at "Footer" Change section name "Get It Touch" to "Get In Touch". | Priya | done
41 | eCommerce Website | On "Home Page" "Get In Touch" section at "Footer" "Twitter" icon click functionality is not working. | Ashish Sir | YTS
42 | eCommerce Website | On "Home Page" "Get In Touch" section at "Footer" "Facebook" icon click functionality is not working. | Ashish Sir | YTS
43 | eCommerce Website | On "Home Page" "Get In Touch" section at "Footer" "instagram" icon click functionality is not working. | Ashish Sir | YTS
44 | eCommerce Website | On "Home Page" "Get In Touch" section at "Footer" "Phone No." icon click functionality is not working. | Ashish Sir | YTS
45 | eCommerce Website | On "Home Page" "Get In Touch" section at "Footer" tooltip for "Twitter" icon is not available. | Priya | done
46 | eCommerce Website | On "Home Page" "Get In Touch" section at "Footer" tooltip for "Facebook" icon is not available. | Priya | done
47 | eCommerce Website | On "Home Page" "Get In Touch" section at "Footer" tooltip for "Instagram" icon is not available. | Priya | done
48 | eCommerce Website | On "Home Page" "Get In Touch" section at "Footer" tooltip for "Phone No" icon is not available. | Priya | done
49 | eCommerce Website | On "Home Page" "Payment Accept" section at "Footer" Can we have icon for "paypal", "VISA" etc. instated of text. Refer Bhajiwala.com | Ashish Sir | YTS
50 | eCommerce Website | On "Home Page" "Payment Accept" section at "Footer" Click functionality is not require for text "paypal", "VISA" etc. so mouse pointer icon should not change when user hover mouse on text. | Priya | done
51 | eCommerce Website | On "Home Page" "Get Newsletter" section at "Footer" Get newsletter functionality is not working. | Ashish Sir | YTS
52 | eCommerce Website | On "Home Page" "Get Newsletter" section at "Footer" Click on "SUBSCRIBE" button, application misbehaves. | Ashish Sir | YTS
53 | eCommerce Website | On "Home Page" at "Footer" Links "Career", "Quality Standard", "FAQ", "Terms And Conditions", "Disclaimer" and "Cancellation & Return Policy" are missing. Refer Bhajiwala.com | Ashish Sir | YTS
54 | eCommerce Website | Require Product images from client. | Manish | YTS
55 | eCommerce Website | Change "Cart" icon. Refer "Bhajiwala.com | Ashish Sir | YTS
56 | eCommerce Website | Modal for asking PIN always appears whenever you revisit to "Home" page. | Priya | Done
57 | eCommerce Website | Prerequisit - You haven't signup for unimadai. Visit to the site. Application has "My Account" link, logically it is wrong as you don’t have account. Application should have "Login¦Signup" links at header. Refer Bhajiwala.com | Priya | YTS
58 | Websit Admin | "Home Page" - Baner functionality management. | Ashish Sir | YTS
59 | Websit Admin | "Home Page" - "Offers" functionality management. (Refer Bhajiwala.com) | Ashish Sir | YTS
60 | Websit Admin | "Home Page" - "Best Deal" functionality management. (Refer Bhajiwala.com) | Ashish Sir | YTS
61 | Websit Admin | "Home Page" - "New Arrival" functionality management. (Refer Bhajiwala.com) | Ashish Sir | YTS
62 | Websit Admin | "Home Page" - "Big Sale" functionality management. | Ashish Sir | YTS
63 | Websit Admin | "Home Page" - Blog management system. | Ashish Sir | YTS
64 | Distribution Management | Review | Madhuri | YTS
65 | Franchise - Auto Stock Update Facility | This is same as Delivery challan. Franchise will click on Accept button for each product delivery. Product prices change on daily basis. So stock must be displayed according to price. | Madhuri | YTS
66 | Admin - Billing Management | Franchise - Bill Prepare a bill with Standard Bill Format. Show Bill Rate & MRP Rate. | Madhuri | YTS
67 | Admin | Reports | Ashish Sir | YTS
68 | Admin | Admin Dashboard | Ashish Sir | YTS
69 | Franchise Login | Franchise Dashboard | Ashish Sir | YTS
70 | Franchise Login | Order Management | Ashish Sir | YTS
71 | Franchise Login | Franchise side Inventory | Ashish Sir | YTS
72 | Franchise Login | Reports | Ashish Sir | YTS
73 | Franchise Login | Billing Management | Ashish Sir | YTS
74 | Admin - Master data | On "Franchise Master" page. Franchise Master table contains should be finalized. For this please discuss with Ashish Sir. | Ashish Sir | YTS
75 | Admin - Master data | Add new page "Supplier Master". | Ashish Sir | YTS
76 | Inventory Management | On "Raw Material Inward" page, "Purchase No." should be system generated. | Madhuri | Done
77 | Inventory Management | On "Raw Material Inward" page, "Details" should not be mandatory. | Madhuri | Done
78 | Inventory Management | On "Raw Material Inward" page, products name in "Select Product" dropdown list should display in assending order. | Madhuri | YTS
79 | Inventory Management | On "Raw Material Inward" page, "Unit Rate" should have "UOM" dropdown. | Madhuri | YTS
80 | Inventory Management | Raw Material Stock Report. Ashish sir please discuss with Mandar sir. | Madhuri | YTS
81 | Admin - Master data | UOM master page all functionality. | Priya | done | 2 | 2020-06-24
82 | Admin - Master data | Tax rate & Tax master page all functionality. | Priya | WIP | 2 | 2020-06-24
83 | Inventory Management | Raw material bulk upload. | Madhuri | WIP | 4 | 2020-06-24
84 | Inventory Management | Finished good bulk upload. | Madhuri | WIP